## Open assigned to me
Type | Id | Summary | Status | Resolution | Defect Recur Frequency | Subsystem | Modified Date | Due Date | Owned By | Priority | Tags | Platform Vehicle Model | Assigned To System | Creation Date | 领域 | 说明 | 模块 | 车型 | 负责人 | 超期/天 | 进展说明（对应模块的研发更新） | 研发状态开发更新 | 提交代码date | 版本时间 | 测试结果 | 测试备注 | 签入日期 | 测试人员
Bug | 993824 | [SystemUI Launcher][VCS A2LL MY24][R5 rebuild-20250218]主页车模页面出现充电口，车窗图标/The main car model page displays charging port and window icons | Resolved 0/4 |  | Once | Kanzi Service | 2025-2-22 上午11:33 |  | 蒋建,Jiang Jian | P2 |  | Alpha/A2LL/MY24 | PATAC | 2025-2-21 下午5:20
Bug | 993418 | [458 48V MY25.5][4M][S][Reissue][0220][CLEA_R5][Setting] 切换深浅色模式，仪表侧辅助视图与设置常用页面车模颜色有明显偏差 Switching between dark and light color modes, the instrument side auxiliary view has a significant deviation from the car model color in the setup common page | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-21 下午8:32 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-2-21 下午4:28
Bug | 993286 | [Cluster_ADAS][L233][MY23] [R5rebuild] Alert 454 水波纹线条不平滑。 | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-22 下午2:13 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY23 BEV 3/L232/MY24 | PATAC | 2025-2-21 下午2:33
Bug | 993059 | [Kanzi Service][MY24][L233][台架]系统内车模颜色不统一 | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-21 下午12:34 |  | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY24 BEV 3/L233/MY24 | PATAC | 2025-2-21 下午12:33
Bug | 993026 | [Kanzi Service][MY24][A2LL][实车]天窗动效与实际不同步 | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-21 上午11:52 |  | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY24 | PATAC | 2025-2-21 上午11:06
Bug | 992945 | [Kanzi Service][Cadi_HF5_Mid_8M_C1UL] The colors of the Cluster side car model and the Android side car model are inconsistent （Cluster侧车模和Android侧车模颜色不一致） | Resolved 3/4 | fixed | Always | Kanzi Service | 2025-2-22 上午8:35 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 |  | Crossover/C1UL-2/MY25 | PATAC | 2025-2-21 上午9:42
Bug | 992745 | [Cluster General][VCS A2LL MY24][R5 rebuild-20250218]辅助视图前机盖开启后车模不对/Auxiliary view: The car model is incorrect when the front hood is opened | Resolved 0/4 |  | Always | Cluster General | 2025-2-20 下午6:50 |  | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY24 | PATAC | 2025-2-20 下午5:42
Bug | 992726 | [Cluster General] [HF5-0218][VCS L233 MY24][VCU]13:57IPC低概率空白后重启。/13: 57IPC has a low probability of being blank before restarting. | 3/4 Reviewed | duplicated | Frequent | Cluster General | 2025-2-20 下午7:20 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 |  | BEV 3/L233/MY24 | PATAC | 2025-2-20 下午5:25
Bug | 992685 | [458 48V MY25.5][4M][S][Reissue][0220][CLEA_R5][Setting] 设置常用页面车模钢圈颜色为黑色，系统页面车模钢圈颜色为银色，两个页面显示不一致 Setting display page car model rim color is black, the system page car model rim color is silver, the two pages display inconsistent | Resolved 0/4 |  | Always | Setting | 2025-2-21 上午10:07 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25.5 | PATAC | 2025-2-20 下午5:04
Bug | 992683 | [458 48V MY25.5][S][0220][clea_r5][Setting]常用中车模应用灰色色块后车模颜色与色块颜色不一致/The commonly used car model uses gray color blocks, but the color of the car model does not match the color of the color blocks | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-20 下午5:50 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25.5 | PATAC | 2025-2-20 下午5:03
Bug | 992650 | [Cluster_Warning][358-2 48V MY26][APPV][0122][clea_r5 mainline][Alert] 速度视图，深色模式下warning#9273触发时，右侧车道线部分无动效 Speed view, no animation on the right lane line part when warning#9273 is triggered in dark mode | Resolved 0/4 |  | Always | Cluster_Warning | 2025-2-20 下午4:50 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2/MY26 | PATAC | 2025-2-20 下午4:48
Bug | 992557 | [Cluster_ADAS][Cluster_Warning][O1SL][MY23][R5rebuild] super cruise 自动变道alert 20210˜2021 在ADAS 视图车道滚动效果图不对。 | Resolved 3/4 | duplicated | Always | Cluster_ADAS | 2025-2-20 下午4:57 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P2 |  | Omega/O1SL-2/MY23 BEV 3/L233/MY23 BEV 3/L232/MY24 | PATAC | 2025-2-20 下午3:51
Bug | 992511 | [557 MY26][APA][VCU]泊车过程中，车模完全被挡在360视图后面 | Resolved 0/4 |  | Always | APA | 2025-2-20 下午8:56 |  | 蒋建,Jiang Jian | P1 |  | U-Van/557/MY26 | PATAC | 2025-2-20 下午3:10
Bug | 992373 | [Cluster_ADAS][A2LL][MY24][HF5]ADAS的3D车模不显示倒车灯效 | Resolved 3/4 | fixed | Always | Cluster_ADAS | 2025-2-20 下午7:34 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY24 BEV 3/L232/MY24 Epsilon/E2QL/MY23 Omega/O1SL-2/MY23.5 | PATAC | 2025-2-20 下午12:56
Bug | 992297 | [Performance][Cluster_Peek-In][Cadi_High_r5_HF5][L23X]P档充电播放动效时，后台peekin进程无法进入Idle模式 / When charging and playing dynamic effects in P mode, the background Peekin process cannot enter Idle mode | Resolved 3/4 | fixed | Always | Performance | 2025-2-20 下午7:20 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 |  | BEV 3/L233/MY24 BEV 3/L232/MY24 BEV 3/L234/MY26 | PATAC | 2025-2-20 上午10:35
Bug | 992293 | [System][E2UB]AL71配置曲线流水灯，和仪表动画不一致 | Resolved 0/4 |  | Once | System | 2025-2-22 上午11:28 |  | 蒋建,Jiang Jian | P2 |  | Epsilon/E2UB/MY24 | PATAC | 2025-2-20 上午10:29
Bug | 992047 | [Cluster_ADAS][Cluster General][557][主线]ADAS视图下，打开转向灯/双闪，3D小车模型的闪烁频率异常 | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-19 下午6:38 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-19 下午4:43
Bug | 992044 | [Vehicle_Control][557][MY26]驾驶模式动效一直播放，不会恢复到默认状态。 | Resolved 0/4 |  | Always | SystemUI Launcher | 2025-2-19 下午7:42 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-19 下午4:41
Bug | 991964 | [Framework][L233][MY24][HF5] 在实况车模中没有显示怀挡和雨刮拨杆 | Resolved 0/4 |  | Always | Framework | 2025-2-19 下午3:53 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 | PATAC | 2025-2-19 下午3:33
Bug | 991952 | [Cluster General] [HF5-0218][VCS L233 MY24][VCU]IPC地图视图切换至辅助视图后，IPC显示空白，无任何内容。/After switching from IPC map view to auxiliary view, IPC displays blank with no content. | Resolved 3/4 | duplicated | Once | Cluster General | 2025-2-20 下午4:48 | 2025-2-19 下午12:00 | 蒋建,Jiang Jian | P2 |  | BEV 3/L233/MY24 | PATAC | 2025-2-19 下午3:20
Bug | 991944 | [System][E2UB]氛围灯页面里的车模，门把手和实车不符 | Resolved 3/4 | fixed | Once | System | 2025-2-21 下午2:05 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 |  | Epsilon/E2UB/MY24 | PATAC | 2025-2-19 下午3:08
Bug | 991943 | [System][E2UB]UB的车窗，kanzi不需要做动画，车模车窗全部关闭状态 | Resolved 0/4 |  | Once | System | 2025-2-21 下午1:39 |  | 蒋建,Jiang Jian | P2 |  | Epsilon/E2UB/MY24 | PATAC | 2025-2-19 下午3:08
Bug | 991930 | [Cluster_Peek-In][cadi-rebuild][L232][hotfix5]peekin显存占用过高【The peekin video memory usage is too high】 | Resolved 3/4 | duplicated | Always | Cluster_Peek-In | 2025-2-20 下午7:21 | 2025-2-20 下午12:00 | 蒋建,Jiang Jian | P2 |  | BEV 3/L232/MY25 | PATAC | 2025-2-19 下午2:51
Bug | 991873 | [Setting] [HF5-0218][VCS L233 MY24][VCU]浅色模式下，显示右侧车模中的后视镜看不到。/In light mode, the rearview mirror in the right car model cannot be seen. | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-21 下午4:23 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 | PATAC | 2025-2-19 下午1:40
Bug | 991826 | [Cluster_ADAS][cadi-rebuild][A2LL][hotfix5]Super Cruise Lane Change车道线异常滚动【Super Cruise Lane Change Abnormal rolling】 | Resolved 1/4 | fixed | Always | Cluster_ADAS | 2025-2-20 下午5:01 | 2025-2-20 下午12:00 | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY25 | PATAC | 2025-2-19 上午11:22
Bug | 991469 | [Kanzi Service][MY24][L233][台架]实况桌面显示灰色阴影 | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-18 下午6:38 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 | PATAC | 2025-2-18 下午6:36
Bug | 991412 | [Setting][MY24][L233][台架]声音tab页面的车模清晰度低，且扶手箱区域与声场平衡车模不一致 | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-18 下午7:04 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 | PATAC | 2025-2-18 下午5:36
Bug | 991321 | [HUD][557][MY26][VC7.0] AR视图下，HUD不显示停止线 | Resolved 0/4 |  | Always | HUD | 2025-2-19 下午3:50 |  | 蒋建,Jiang Jian | P1 |  | U-Van/557/MY26 | PATAC | 2025-2-18 下午4:45
Bug | 991104 | [Vehicle_Control][557][MY26]天窗遮阳帘“关闭”button显示样式不对。 | Resolved 0/4 |  | Always | SystemUI Launcher | 2025-2-19 下午2:10 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-18 下午2:14
Bug | 990833 | [Kanzi Service][MY24][L233][台架]实况桌面，MY24 L233车模开门后，显示的实体启动按键 | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-17 下午9:08 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 | PATAC | 2025-2-17 下午9:05
Bug | 990806 | [Energy][MY24][L233][台架]充电中，实况桌面与能量中心页面来回切换，切换效果不流畅 | Resolved 3/4 | fixed | Always | Energy | 2025-2-20 下午7:27 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 |  | BEV 3/L233/MY24 | PATAC | 2025-2-17 下午8:39
Bug | 990754 | [INC_Service][557 MY26][VCUPro][Vescom7.0][Mainline]浅色模式下实况桌面转动车模,车模轮胎倒影闪现花屏\Light color mode live desktop rotation model, model tire reflection flash flower screen | Resolved 0/4 |  | Always | INC_Service | 2025-2-18 下午2:24 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-2-17 下午7:39
Bug | 990659 | [vcupro_main][557][MY26][Smoke Test][Clea][Climate] The Cadi car model was display in climate screen （空调页面显示凯迪车模） | Resolved 3/4 | fixed | Always | Kanzi Service | 2025-2-21 下午5:55 | 2025-2-26 下午12:00 | 蒋建,Jiang Jian | P2 | zy_transferred_0217 | U-Van/557/MY26 | PATAC | 2025-2-17 下午5:46
Bug | 990568 | [Cluster_Warning][358-2 48V MY26][APPV][0122][clea_r5 mainline][Alert] Warning #334‘充电门未关’充电门显示在车模左侧 Warning #334 charging door shown on left side of car model | Resolved 0/4 |  | Always | Cluster_Warning | 2025-2-17 下午5:12 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2/MY26 | PATAC | 2025-2-17 下午4:31
Bug | 990069 | [Performance]压力测试中，com.patac.launcher出现crash | Resolved 0/4 | fixed | Once | Performance | 2025-2-18 下午1:52 | 2025-2-17 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-15 下午6:00
Bug | 990059 | [Performance]压力测试后，实况桌面车模消失 | Resolved 0/4 |  | Once | Performance | 2025-2-20 下午5:19 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-15 下午4:45
Bug | 990056 | [Performance]压力测试中，com.ts.kanziservice 内存平均值和峰值均超出kpi，同时出现anr | Resolved 0/4 |  | Once | Performance | 2025-2-19 下午6:58 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-15 下午4:15
Bug | 990052 | [Cluster_ADAS][L233][MY24][HF5]安卓显示充电门打开，IPC显示关闭着，两边显示不一致 | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-15 下午4:04 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 | PATAC | 2025-2-15 下午4:03
Bug | 990031 | [Vehicle Setting][MY24][A2LL][台架]辅助驾驶页面的车模与车道线比例与真实世界不一致 | Resolved 0/4 |  | Always | Vehicle Setting | 2025-2-15 下午1:53 |  | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY24 | PATAC | 2025-2-15 下午12:32
Bug | 989819 | [Cluster_Warning][358-2 48V MY26][APPV][0122][clea_r5 mainline][Alert] Warning #9253-#9255 触发时，车顶上的刹车图标会闪烁 Warning #9253-#9255 When triggered, the brake icon on the roof of the car flashes | Resolved 0/4 |  | Always | Cluster_Warning | 2025-2-14 下午5:51 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2/MY26 | PATAC | 2025-2-14 下午5:06
Bug | 989750 | [System][E2UB MY24]驾驶辅助模式车模状态和实际状态不一致 | Resolved 0/4 | fixed | Once | System | 2025-2-14 下午4:18 |  | 蒋建,Jiang Jian | P2 |  | Epsilon/E2UB/MY24 | PATAC | 2025-2-14 下午4:10
Bug | 989692 | [Cluster_Peek-In]L233[MY23][R5_rebuild]在Peekin 动效 页面，在车标未完全显示之前，屏幕的左侧和右侧分别用一条直线显示。 | Resolved 3/4 | fixed | Always | Cluster General | 2025-2-20 下午4:40 | 2025-2-20 下午12:00 | 蒋建,Jiang Jian | P2 |  | BEV 3/L233/MY23 | PATAC | 2025-2-14 下午3:16
Bug | 989505 | [Climate][Cadi_R5_HF5_Mid_8M_Rebuild]During the process of running Monkey, the display mode of the air conditioning interface is inconsistent with the IPC(跑monkey过程中空调界面显示模式与仪表不一致) | Resolved 0/4 |  | Once | Framework | 2025-2-17 下午4:07 |  | 蒋建,Jiang Jian | P3 | lg_transferred_0214, fw_ts | BEV 3/L233/MY25 | PATAC | 2025-2-14 上午11:28
Bug | 989237 | [SystemUI Launcher][358-2 48V/PHEV MY25][CIP6][0127][clea_r5][SystemUI Launcher ]车模界面，通过Dock栏切换到媒体界面，车模消失较慢。\The car model interface, switch to the media interface through the Dock bar, and the car model disappears slowly. | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-19 上午9:21 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2/MY25 U-Van/358-2 PHEV/MY25 | PATAC | 2025-2-13 下午6:27
Bug | 988511 | [Setting][557 MY26][VCUPro][Vescom7.0][Mainline]偶现进入设置项HMI半边屏幕显示黑屏\A black screen is displayed on the half of the HMI screen | Resolved 3/4 | reject-cannot reproduce | Once | Kanzi Service | 2025-2-21 上午11:10 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-12 下午7:33
Bug | 988453 | [Climate][B233 MY25][Mid]进入空调面板/座椅面板时，车模会闪烁 | Resolved 0/4 |  | Frequent | Kanzi Service | 2025-2-13 上午9:28 |  | 蒋建,Jiang Jian | P2 | sq_transferred_0213 | BEV 3/B233/MY25 BEV 3/B223/MY25 Epsilon/E2UB/MY24 Epsilon/E2YB/MY24 | PATAC | 2025-2-12 下午5:52
Bug | 988374 | [Cluster_Warning][358-2 48V MY26][APPV][0122][clea_r5 mainline][Alert] 前雷达故障时，触发的Warning #2中，车模示红的区域未覆盖到全部前雷达 In Warning #2 triggered when the front radar fails, the area shown in red by the car model does not cover all of the front radar | Resolved 0/4 |  | Always | Cluster_Warning | 2025-2-12 下午6:20 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2/MY26 | PATAC | 2025-2-12 下午5:00
Bug | 988047 | [Setting][L232][MY24]歌曲的音效设置和setting部分的音效设置表现情况不一致 | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-13 上午10:30 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L232/MY24 BEV 3/L233/MY26 | PATAC | 2025-2-12 下午2:42
Bug | 988029 | [Climate][358-2phev][clea_my26]HMI空调界面正面出风不显示动画 | Resolved 3/4 | fixed | Frequent | Kanzi Service | 2025-2-18 上午9:43 | 2025-2-18 下午12:00 | 蒋建,Jiang Jian | P2 | zy_transferred_0214 | U-Van/358-2/MY26 | PATAC | 2025-2-12 下午2:25
Bug | 987979 | [557][Setting]浅色模式，设置页面所有tab菜单不可见 | Resolved 0/4 |  | Once | Kanzi Service | 2025-2-12 下午8:56 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-2-12 下午1:46
Bug | 987579 | [Framework][MY23] [L233] [实车] 从setting退出到实况桌面，车模车窗会出现开窗动效。 | Resolved 0/4 |  | Always | Framework | 2025-2-12 下午3:36 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY23 | PATAC | 2025-2-12 上午10:00
Bug | 987567 | [Vehicle Setting][557][MY26]Home页面车模显示不全。 | Resolved 0/4 |  | Frequent | SystemUI Launcher | 2025-2-20 下午6:33 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-12 上午9:48
Bug | 987244 | [Cluster_PowerMode][MY24][L233][台架]power mode 从 propulsion切换至off,再开门,凯迪大图标外围有齿轮状 | Resolved 3/4 | fixed | Always | Cluster_PowerMode | 2025-2-20 下午7:29 | 2025-2-21 下午12:00 | 蒋建,Jiang Jian | P2 | 0214close | BEV 3/L233/MY23 BEV 3/L233/MY24 | PATAC | 2025-2-11 下午4:43
Bug | 987201 | [358-2 48V/PHEV MY25][CIP6][0127][clea_r5][Climate]空调界面显示的出风动效与实际车辆出风口状态不一致/The aerodynamic effect displayed on the air conditioning interface is inconsistent with the actual state of the vehicle's air outlet | Resolved 0/4 |  | Frequent | Kanzi Service | 2025-2-11 下午6:16 |  | 蒋建,Jiang Jian | P3 | zy_transferred_0211 | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25 | PATAC | 2025-2-11 下午4:03
Bug | 986526 | HMI_PA warning display wrong region | Resolved 0/4 |  | Always | Cluster_Telltale | 2025-2-19 下午6:30 | 2025-2-18 下午1:42 | 蒋建,Jiang Jian | P2 |  | U-Van/458/MY23 | PATAC | 2025-2-11 下午1:42
Bug | 986116 | VESCOM6.0 demo 泊车页面退出后先进壁纸桌面再进车模页面-null | Resolved 3/4 | fixed | Always | System | 2025-2-19 下午7:30 | 2025-3-11 上午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-10 下午11:14
Bug | 986004 | [Cluster General][Rebuild-0205][VCS L233 MY26][VCU]辅助视图车模显示不全，The auxiliary view model is not fully displayed | Resolved 3/4 | duplicated | Always | Cluster General | 2025-2-13 下午1:20 | 2025-2-14 下午12:00 | 蒋建,Jiang Jian | P2 | my26sopunique | BEV 3/L233/MY26 | PATAC | 2025-2-10 下午5:50
Bug | 985568 | [557E][MY26][ADAS Settings]ADAS界面的NOP图标与其他界面重叠 | Resolved 3/4 | fixed | Frequent | Kanzi Service | 2025-2-19 上午7:44 | 2025-2-13 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-2-10 下午2:44
Bug | 985036 | [Setting][557 MY26][VCUPro][Vescom7.0][Mainline]进入设置部分Tab页中车模重叠/Go to the Settings Tab page to overlap models | Resolved 3/4 | duplicated | Always | Kanzi Service | 2025-2-18 下午1:57 | 2025-2-18 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-8 下午4:40
Bug | 984909 | [Cluster_ADAS][Cadi_f1kh_r5_HF5][A2LL]灯光效果在P档放大显示 / The lighting effect is enlarged and displayed in P mode | Resolved 3/4 | fixed | Always | Cluster_ADAS | 2025-2-10 下午3:53 | 2025-2-14 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY26 Epsilon/E2UL/MY24 BEV 3/L233/MY24 Epsilon/E2QL/MY24 BEV 3/L232/MY24 Omega/O1SL-2/MY24 Alpha/A2LL/MY24 | PATAC | 2025-2-8 下午2:41
Bug | 984654 | [458 48V MY23][4M][CIP6][0107][CLEA_R5][Setting]休眠重启冷启动，打开设置-通用-声音界面闪现车模。\Hibernate and restart cold start, open Settings - General - Sound interface flashes the car model. | Resolved 0/4 |  | Frequent | Kanzi Service | 2025-2-18 下午3:35 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY23 | PATAC | 2025-2-7 下午6:47
Bug | 984653 | [458 48V MY23][4M][CIP6][0107][CLEA_R5][Ambient_Light]休眠重启设置中的氛围灯和实车氛围灯不一致。\The ambient light in the sleep restart setting is inconsistent with the ambient light of the actual car. | Resolved 0/4 | duplicated | Frequent | Kanzi Service | 2025-2-19 下午7:28 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY23 | PATAC | 2025-2-7 下午6:43
Bug | 984571 | [Climate][CLEA_R5][MY25][358]点击电动出风口的关闭按钮再单击打开，主驾/副驾两侧出风口均关闭/均打开 | Resolved 0/4 |  | Always | Climate | 2025-2-21 下午4:32 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY26 U-Van/358-2/MY25 | PATAC | 2025-2-7 下午5:13
Bug | 984468 | [LCDD][MY25 A2LL]14：26 机盖打开后车模无机舱细节 | Resolved 3/4 | fixed | Always | LCDD | 2025-2-12 上午8:32 | 2025-2-14 下午12:00 | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY25 | PATAC | 2025-2-7 下午3:52
Bug | 984283 | [358-2 48V/PHEV MY25][CIP6][0127][clea_r5][Climate]点击主（副）驾上任一出风口时，另一出风口关闭/打开效果自动不显示，需要手动点击该位置时才显示/When clicking on either air outlet of the driver (or passenger), the effect of closing/opening the other air outlet will not be displayed automatically. It will only be displayed when manually clicking on that position | Resolved 0/4 |  | Always | Kanzi Service | 2025-2-7 上午9:57 |  | 蒋建,Jiang Jian | P3 | zy_transferred_0207 | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25 | PATAC | 2025-2-7 上午9:36
Bug | 984271 | [358-2 48V/PHEV MY25][CIP6][0127][clea_r5][Climate]空调吹风模式从自动切换到其他模式后无出风口打开和关闭时的动效显示/Dynamic display when there is no air outlet opening or closing when the air conditioning blowing mode switches from automatic to other modes | Resolved 0/4 |  | Frequent | Kanzi Service | 2025-2-8 上午10:58 |  | 蒋建,Jiang Jian | P3 | sq_transferred_0207 | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25 | PATAC | 2025-2-7 上午9:11
Bug | 984270 | [Climate][CLEA_R5][MY25][358]开启/关闭单侧出风口，另一侧风道口圆圈消失 | 3/4 Reviewed | duplicated | Always | Kanzi Service | 2025-2-11 下午3:40 | 2025-2-11 下午12:00 | 蒋建,Jiang Jian | P2 | zy_transferred_0207 | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY26 U-Van/358-2/MY25 | PATAC | 2025-2-7 上午9:08
Bug | 984224 | [Setting][458 48V MY25.5][4M][S 1.0][0110][CLEA_R5][Setting]旋转氛围灯灯球后立即关闭氛围灯，氛围灯自动开启\ Turn off the ambient light immediately after rotating the ambient light ball, and the ambient light will turn on automatically | Resolved 0/4 |  | Once | Ambient_Light | 2025-2-19 下午2:52 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-2-6 下午7:42
Bug | 984207 | [557][Energy][MY26][main]充电界面车模与设置界面车模重叠 | Resolved 3/4 | duplicated | Always | Kanzi Service | 2025-2-18 下午2:12 | 2025-2-18 下午12:00 | 蒋建,Jiang Jian | P2 | zzl_transferred_0207 | U-Van/557/MY26 | PATAC | 2025-2-6 下午6:27
Bug | 984181 | [SystemUI Launcher][VCS A2LL MY24][R5 rebuild-20250205]点击设置按钮，主界面车模概率性闪烁/Click the settings button, and the main interface of the car model will flash probabilistically | Resolved 0/4 |  | Frequent | SystemUI Launcher | 2025-2-11 下午4:20 |  | 蒋建,Jiang Jian | P3 |  | Alpha/A2LL/MY24 | PATAC | 2025-2-6 下午5:30
Bug | 983853 | hmi-车模主页面-模式-舒适模式无动画-null | Resolved 0/4 |  | Always | System | 2025-2-6 下午5:10 | 2025-3-5 上午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-5 下午4:33
Bug | 983781 | hmi-车模主页面-功能选项按钮丢失-null | 3/4 Reviewed | fixed | Frequent | Kanzi Service | 2025-2-18 下午9:12 | 2025-3-5 上午12:00 | 蒋建,Jiang Jian | P1 |  | U-Van/557/MY26 | PATAC | 2025-2-5 下午2:44
Bug | 983727 | [Performance] 压测期间com.patac.hmi.climate出现了anr | Resolved 0/4 |  | Once | Performance | 2025-2-13 下午1:22 |  | 蒋建,Jiang Jian | P2 | lg_transferred_0210 | U-Van/557/MY26 | PATAC | 2025-2-5 下午12:19
Bug | 983718 | [CT] [VCUPro] 车机启动后出现 LCDD Data Provisioning 丢失的画面 | Resolved 0/4 |  | Frequent | PowerMode | 2025-2-13 下午1:22 | 2025-2-12 下午12:01 | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-2-5 下午12:01
Bug | 983565 | [Performance][557]Power Cycle测试过程中，Launcher进程发生了一次crash | Resolved 0/4 | fixed | Once | Performance | 2025-2-19 上午8:23 | 2025-2-17 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-2-2 下午3:35
Bug | 983488 | [Setting]powercycle 压力测试中，setting页面重叠在一起 | Resolved 3/4 | duplicated | Once | Kanzi Service | 2025-2-18 下午2:53 | 2025-2-18 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-1-27 下午11:02
Bug | 983076 | [458 48V MY23][4M][R2 HF1][0116][Cluster_ADAS]仪表驾驶辅助视图，识别的车道线动画显示有锯齿。\Instrument Assist view, with a jagged animated display of recognized lane markings. | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-1-24 下午5:14 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY23 | PATAC | 2025-1-24 下午4:22
Bug | 982100 | [Cluster_ADAS][Cadi_f1km_r5_HF5][L233]adas路面竖条摩尔纹严重 / ADAS road surface has severe vertical stripes and moir é patterns | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-9 下午4:37 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY24 Omega/O1SL-2/MY24 | PATAC | 2025-1-22 下午5:25
Bug | 981763 | [Cluster_ADAS][557][80BOR]无法激活LKA 干预状态左右两车道线警示色常亮 / Unable to activate LKA intervention status, the warning colors of the left and right lane lines are constantly on | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-1-22 下午1:39 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-1-22 上午11:52
Bug | 981751 | [APA]偶发泊车过程中点击可用车位VCU 弹窗提示‘该车位无法泊入’ | Resolved 3/4 | fixed | Once | APA | 2025-2-17 下午3:44 | 2025-2-13 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-1-22 上午11:17
Bug | 981535 | [458 48V MY23][4M][R5 HF1][0107][HUD]HUD切换到驾驶辅助图视，HUD车道线显示有锯齿。\The HUD switches to the driver assistance view, and the HUD lane markings are displayed with aliases. | Resolved 3/4 | fixed | Always | HUD | 2025-2-10 上午11:05 | 2025-2-10 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY23 | PATAC | 2025-1-21 下午5:51
Bug | 981499 | [458 48V MY23][4M][R5 HF1][0107][Cluster_Gauge]P档下切换车模颜色，仪表车模未成功切换。\Switch the color of the car model under P gear, and the instrument car model is not successfully switched. | Resolved 0/4 |  | Always | Cluster_Gauge | 2025-1-24 下午1:22 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY23 | PATAC | 2025-1-21 下午5:28
Bug | 981450 | [Cluster General] [458 48V MY25.5][S][0110][clea_r5][Cluster]仪表辅助视图，车模颜色为蓝/白色时，仪表侧车模后方没有阴影显示。/Gauge assist view, when the model color is blue/white, there is no shadow behind the model car on the instrument side. | Resolved 0/4 |  | Always | Cluster General | 2025-1-21 下午5:58 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-1-21 下午4:55
Bug | 980874 | [APA][557 MY26][VeSCoM5.0][LVM]从360界面点击自动泊车图标进入自动泊车界面过程中，会先闪退进主页，在进入自动泊车界面/When clicking on the automatic parking icon from the 360 interface to enter the automatic parking interface, it will first flash back to the homepage, and then enter the automatic parking interface | Resolved 0/4 |  | Once | LVMAPA | 2025-2-20 下午3:26 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-1-20 下午5:54
Bug | 980425 | [557E MY26][VeSCoM5.0][VCU Pro][APA] 垂直空间车位-车位搜索过程中未释放车位 | Resolved 0/4 |  | Always | LVMAPA | 2025-2-19 下午4:18 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-1-20 上午9:59
Bug | 980061 | [Basic_Module][Setting][458 48V MY25.5][4M][S 1.0][0111][CLEA_R5][Setting]仪表侧部分车模颜色的倒影显示异常（灰色显示)\ The reflection of the color of the car model in the instrument measurement part is abnormal (gray display) | Resolved 0/4 |  | Always | Kanzi Service | 2025-1-23 下午7:03 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-1-17 下午5:28
Bug | 980040 | [358-2 48V MY26][IV造车][1221][clea_r5 mainline][Climate] 深色模式下，座椅/空调页面切换，前风挡出风口闪吹风动效 In dark color mode, the seat/air conditioning page switches, and the front windshield vents flash blowing air kinetic effect | Resolved 0/4 |  | Always | Climate | 2025-1-17 下午5:53 |  | 蒋建,Jiang Jian | P3 | lg_transferred_0117 | U-Van/358-2/MY26 | PATAC | 2025-1-17 下午5:17
Bug | 979914 | [Ambient_Light][CLEA_R5][MY25][458][4M] 后排调节氛围灯亮度，前排偶现未同步调节 | Resolved 0/4 |  | Frequent | Ambient_Light | 2025-1-17 下午8:28 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY26 U-Van/458/MY25.5 U-Van/458/MY25 | PATAC | 2025-1-17 下午3:24
Bug | 979894 | [Ambient_Light][358-2 48V/PHEV MY25.6][S2][1231][clea_r5][Ambient light]氛围灯车模与实车显示不一致（车模上未显示无线充电部分氛围灯效果）/The atmosphere light model does not match the actual car display (the wireless charging part of the atmosphere light effect is not displayed on the model) | Resolved 0/4 |  | Always | Ambient_Light | 2025-1-17 下午3:10 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25 | PATAC | 2025-1-17 下午2:58
Bug | 979566 | [Ambient_Light][458 48V MY23][4M][CIP6][0107][CLEA_R5][Ambient_Light]休眠重启，浅色模式首次进入氛围灯车模界面会闪现深色模式的车模背景。\Hibernate and restart, the light mode enters the ambient light for the first time, and the car model interface will flash the background of the car model in dark mode. | Resolved 0/4 |  | Always | Ambient_Light | 2025-2-6 上午9:32 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25.5 U-Van/458/MY23 | PATAC | 2025-1-17 上午9:34
Bug | 979466 | [Cluster_ADAS][557]LCC变道激活引导线效果异常 / LCC lane change activation guide line effect is abnormal | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-1-16 下午8:18 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-1-16 下午8:17
Bug | 979356 | [LVMAPA][vcupro_main][557][MY26][Smoke Test]打开LVM，影像区未正常显示(When LVM is turned on, the image area does not wake up properly) | Resolved 3/4 | fixed | Always | LVMAPA | 2025-2-18 下午2:53 | 2025-2-11 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-1-16 下午5:45
Bug | 979319 | [Setting][458 48V MY25.5][4M][S 1.0][0111][CLEA_R5][Setting]双拼色车模色板镜像部分显示错误，无双拼色效果\ The mirror part of the double color car model color palette is displayed incorrectly, and there is no double color matching effect | Resolved 0/4 |  | Always | UI Framework | 2025-1-17 下午2:27 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-1-16 下午5:21
Bug | 979313 | [Setting][458 48V MY25.5][4M][S 1.0][0111][CLEA_R5][Setting]双拼色车模上半部显示有色差\ The upper half of the double-color car model shows color difference | Resolved 0/4 |  | Always | UI Framework | 2025-1-17 下午2:36 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-1-16 下午5:18
Bug | 979284 | [Setting][458 48V MY25.5][4M][S 1.0][0111][CLEA_R5][Setting]车模轮胎黄色车圈显示错误\ The yellow rim of the model tires is displayed incorrectly | Resolved 0/4 |  | Always | UI Framework | 2025-1-17 上午9:51 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-1-16 下午5:04
Bug | 979277 | [358-2 48V MY26][IV造车][1221][clea_r5 mainline][Climate] 车辆休眠冷启动，深色模式下首次打开空调页面，空调车模闪现白色 Vehicle hibernation cold start, first time open the air conditioning page in dark mode, the air conditioning module flashes white | Resolved 0/4 |  | Always | UI Framework | 2025-1-16 下午5:07 |  | 蒋建,Jiang Jian | P3 | lg_transferred_0116 | U-Van/358-2/MY26 | PATAC | 2025-1-16 下午4:58
Bug | 977927 | 更新[CLEA][458][R5][Camera]--360, apa some of the car models are the wrong color--360，apa部分车模颜色有误 | Resolved 3/4 | fixed | Always | APA | 2025-2-8 下午3:32 | 2025-2-8 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY23 | PATAC | 2025-1-14 下午5:22
Bug | 977778 | [Cluster General[L233][MY23][R5_rebuild]The line on vehicle model for L233 does not show smoothly in Peek-in(L233 的车模在Power off 视图，部分线条显示锯齿状） | Resolved 0/4 |  | Always | Cluster General | 2025-2-8 下午2:05 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/L233/MY23 | PATAC | 2025-1-14 下午3:44
Bug | 977331 | [Cluster_ADAS][L234][mainline][SC]GB SuperCruise 4025_LaneSegment不显示连成线的水马、红色车道线和道路边沿粗细不一致 / GB SuperCruise 4025_LaneSegment do not display water horses connected by lines, red lane lines, and uneven thickness of road edges | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-9 下午4:42 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L234/MY26 | PATAC | 2025-1-13 下午6:51
Bug | 977319 | [Cluster_ADAS][L234][mainline][SC]GB SuperCruise 4022_Fencing 接口无效果显示 / GB SuperCruise 4022_Fencing interface has no display effect | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-9 下午4:42 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L234/MY26 | PATAC | 2025-1-13 下午6:39
Bug | 977314 | [Cluster_ADAS][L234][mainline][SC]GB SuperCruise 4014 UC_State=0 不显示Super Cruise单车道 / GB SuperCruise 4014 UC_State=0 do not display Super Cruise single lane | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-9 下午4:46 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L234/MY26 | PATAC | 2025-1-13 下午6:31
Bug | 977233 | [Cluster_ADAS][L234][mainline][SC]GB SuperCruise 4013_LaneChange 只显示开始变道和变道完成两种效果 / GB SuperCruise 4013_LaneChange only display two effects: starting lane change and completing lane change | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-9 下午4:47 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L234/MY26 | PATAC | 2025-1-13 下午5:34
Bug | 977138 | [RCC_Vehicle Control][458 48V MY25.5][4M][S 1.0][0107][CLEA_R5][Vehicle_Control]座椅界面点击方向盘加热按钮无响应，但是点击Dock里方向盘加热可以打开和关闭。\Clicking on the steering wheel heating button on the seat interface does not respond, but clicking on the steering wheel heating in the Dock can turn it on and off. | Resolved 0/4 |  | Once | UI Framework | 2025-1-16 下午2:56 |  | 蒋建,Jiang Jian | P3 | lg_transferred_0114 | U-Van/458/MY25.5 | PATAC | 2025-1-13 下午4:33
Bug | 976969 | [Cluster General][vcupro_main][557][MY26][Smoke Test]设置内不同功能车模显示会叠加覆盖在一起（The display of different functions in the settings will be superimposed on top of each other） | Resolved 3/4 | fixed | Always | Cluster General | 2025-2-18 下午1:52 | 2025-2-17 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-1-13 下午2:33
Bug | 976770 | [Vehicle Setting][557][MY26]主页驾驶模式动效显示错误。（Homepage sports mode motion display error.） | Resolved 0/4 |  | Always | Kanzi Service | 2025-1-23 下午7:43 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-1-13 上午11:01
Bug | 976323 | 吹风效果图不对 | 3/4 Reviewed | fixed | Always | Climate | 2025-2-21 下午6:02 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 | cadiq1ux, cadi0109还原度 | BEV 3/L232/MY24 | PATAC | 2025-1-10 下午6:34
Bug | 976057 | [Ambient_Light][458 48V MY25.5][4M][S 1.0][1218][CLEA_R5][Ambient_Light]氛围灯颜色为自动自定义颜色时，开关氛围灯概率性氛围灯选中状态丢失/ When the color of the ambient light is automatically customized, the selected status of the ambient lamp will be lost due to the probability of turning on and off the ambient light | Resolved 0/4 |  | Frequent | Ambient_Light | 2025-1-10 下午6:57 |  | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 | PATAC | 2025-1-10 下午3:33
Bug | 975432 | [HUD][557]ARHUD未正确显示目的地图标、停车场图标、服务区图标、地标建筑图标/The ARHUD does not correctly display the destination map icon, parking lot icon, service area icon, and landmark building icon. | Resolved 0/4 |  | Always | HUD | 2025-1-16 下午7:31 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-1-9 下午4:34
Bug | 974517 | [Ambient_Light][358-2 48V/PHEV MY25.6][S2][1231][clea_r5][AmbientLight]休眠启动后实车氛围灯与设置中氛围灯车模、色球显示颜色不一致/After starting the sleep mode, the actual car's ambient light does not match the color displayed on the car model and color ball in the settings | Resolved 0/4 |  | Frequent | Ambient_Light | 2025-1-10 下午4:20 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2 PHEV/MY25 | PATAC | 2025-1-8 下午5:13
Bug | 974416 | [Setting][B233 MY25][Mid]修改常用中车模角度，进入氛围灯后返回常用页面，车模状态未保持/Modify the angle of commonly used car models, return to the commonly used page after entering the ambient light, but the car model status is not maintained | Resolved 3/4 | duplicated | Always | Setting | 2025-1-9 下午5:30 | 2025-2-6 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/B233/MY25 BEV 3/B233/MY24 BEV 3/B223/MY25 | PATAC | 2025-1-8 下午4:15
Bug | 974009 | [PowerMode][557][80BOR]vcu启动时副驾屏延时1s左右点亮&中控页面加载异常 | Resolved 0/4 |  | Once | PowerMode | 2025-1-16 下午4:42 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2025-1-8 上午10:20
Bug | 973725 | [Vehicle Setting][Rebuild-0101][VCS L232 MY24][VCU]个性化模式车辆设置页字体与个性化驾驶图标重叠/The Personalization mode vehicle settings page font overlaps with the Personalization Driving icon | Resolved 3/4 | fixed | Always | Vehicle Setting | 2025-2-9 下午4:15 | 2025-2-9 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L232/MY24 BEV 3/L233/MY26 | PATAC | 2025-1-8 上午9:49
Bug | 973689 | [Setting][B2X3 8M MY25][R5 HF4][VCU]修改常用中车模角度，进入氛围灯后返回常用页面，车模状态未保持/Modify the angle of commonly used car models, return to the commonly used page after entering the ambient light, but the car model status is not maintained | Resolved 0/4 |  | Always | Setting | 2025-1-8 下午4:56 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/B233/MY25 BEV 3/B233/MY24 | PATAC | 2025-1-8 上午9:12
Bug | 973644 | HMI主页车模点击遮阳帘后车模变大，转动车门按键被遮挡-null | Resolved 3/4 | fixed | Once | System | 2025-2-14 上午6:55 | 2025-2-7 上午12:00 | 蒋建,Jiang Jian | P2 | import_20250114 | U-Van/557/MY26 | PATAC | 2025-1-7 下午9:46
Bug | 972358 | [Ambient_Light] [358-2 48V/PHEV MY26][IV造车][1221][clea_r5 maline][Ambient light]氛围灯场景联动中选项全部开启时，名称显示排序错误。/When all the options are enabled in the ambient light scene linkage, the names are displayed in the wrong order. | Resolved 0/4 |  | Always | Ambient_Light | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2/MY26 | PATAC | 2025-1-6 下午4:58
Bug | 972324 | [Cluster_ADAS][MY26][557E][80BOR][UPA]触发UPA,adas view下,显示范围偏小,提醒效果弱/When UPA is triggered and adas view is triggered, the display range is small and the reminder effect is weak | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2025-1-6 下午4:38
Bug | 971599 | [Cluster_ADAS][CadiRebuild][L232][R5]主驾门关闭开启时，副驾及右后门会闪烁 / When the driver's door is closed or opened, the passenger seat and right rear door will flash | Resolved 0/4 |  | Always | Cluster_ADAS | 2025-2-16 下午4:44 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L232/MY25 | PATAC | 2025-1-3 下午5:03
Bug | 971011 | [358-2 PHEV MY26][IV造车][1221][clea_r5 mainline][Ambient_Light] 氛围灯关闭时，氛围灯场景联动选项没有灰显，选项可以开关但无法编辑 Ambient light scene linkage options are not grayed out when ambient light is off, options can be switched on and off but not edited | Resolved 0/4 |  | Always | Ambient_Light | 2025-1-10 下午6:23 |  | 蒋建,Jiang Jian | P3 |  | U-Van/358-2 PHEV/MY25 | PATAC | 2025-1-2 下午5:05
Bug | 970696 | [Climate][B233 MY25][Mid]切换空调面板和座椅面板时，会一瞬出现上次打开时的面板界面 When switching between the air conditioning panel and the seat panel, the panel interface from the last time it was turned on will appear instantly | Resolved 3/4 | duplicated | Always | UI Framework | 2025-2-8 下午2:29 | 2025-3-7 下午12:00 | 蒋建,Jiang Jian | P2 | sq_transferred_0102 | BEV 3/B233/MY25 BEV 3/B233/MY24 BEV 3/B223/MY25 | PATAC | 2025-1-2 下午1:18
Bug | 970682 | [Climate][Hotfix4][B2X3 MY24 OTA] 座椅加热和通风button颜色深浅不一致（Heated and ventilated seatbutton color shade inconsistency） | Resolved 3/4 | fixed | Always | Climate | 2025-2-20 下午5:58 | 2025-1-21 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/B233/MY24 BEV 3/B223/MY24 | PATAC | 2025-1-2 下午12:17
Bug | 970633 | [Climate][Hotfix4][B2X3 MY24 OTA] 进入/退出空调或座椅Overlay，界面闪烁（Entering/exiting air conditioning or seat Overlay, the interface blinks） | Resolved 3/4 | duplicated | Always | Climate | 2025-2-8 下午2:29 | 2025-2-13 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/B233/MY24 BEV 3/B223/MY24 | PATAC | 2025-1-2 上午10:50
Bug | 970080 | [Climate][B233 MY25][Mid]进入座椅界面，座椅界面会闪烁 Entering the seat interface, the seat interface will flash | Resolved 3/4 | duplicated | Frequent | UI Framework | 2025-2-8 下午2:30 | 2025-3-6 下午12:00 | 蒋建,Jiang Jian | P3 | sq_transferred_1231 | BEV 3/B233/MY25 BEV 3/B233/MY24 BEV 3/B223/MY25 | PATAC | 2024-12-31 下午5:00
Bug | 970069 | [Climate][458 48V MY25.5][4M][S 1.0][1219][CLEA_R5][Climate]切换深浅模式，进入空调界面会闪烁上个深浅模式的背景。\Switch the light mode, and the background of the previous light mode will flash when entering the air conditioner interface. | Resolved 0/4 |  | Frequent | UI Framework | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 | sq_transferred_1231 | U-Van/458/MY25.5 | PATAC | 2024-12-31 下午4:53
Bug | 969953 | [vcupro_main_80BOR][557][MY26][Smoke Test][Clea][System] The process crash about com.ts.kanziservice (com.ts.kanziservice 进程崩溃) | Resolved 0/4 |  | Frequent | System | 2025-1-9 下午4:29 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2024-12-31 下午3:28
Bug | 968699 | [Framework][Launcher][557E][MY26]浅色模式下，实况桌面底图异常，状态栏看不清/In light color mode, the bottom image of the live desktop is abnormal and the status bar is not visible | Resolved 0/4 |  | Once | Framework | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2024-12-30 上午10:35
Bug | 968694 | [Climate][458 48V MY25.5][4M][S 1.0][1218][CLEA_R5][Climate]开启座椅通风加热后再次进入空调页面，瞬时显示座椅页面/ After turning on the seat ventilation and heating, you will enter the air conditioning page again, and the seat page will be displayed instantly | Resolved 3/4 | duplicated | Frequent | UI Framework | 2025-2-8 下午4:27 | 2025-2-14 下午12:00 | 蒋建,Jiang Jian | P3 | lg_transferred_1230 | U-Van/458/MY25 | PATAC | 2024-12-30 上午10:34
Bug | 968429 | [FROM_DevVal][E2UB MY24][VeSCoM22.0][VCU]VR调节氛围灯颜色，VCU界面有70%概率不变化，和灯带显示不一致/VR adjusts the color of the ambient light, and the VCU interface has a 70% probability of no change, which is inconsistent with the display of the light strip | Resolved 0/4 |  | Always | Ambient_Light | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 | devval, from_comm | Epsilon/E2UB/MY24 | PATAC | 2024-12-28 下午3:37
Bug | 968205 | [358-248V/PHEV MY25.5][S][1218][clea_r5][Climate] 空调页面车模中音响上有BOSE字标，与实车不一致 Air conditioning page in the car model of the stereo on the BOSE word mark, not consistent with the real car | Resolved 0/4 |  | Always | UI Framework | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 | lg_transferred_1227 | U-Van/358-2/MY25 U-Van/458/MY25 | PATAC | 2024-12-27 下午5:17
Bug | 968199 | [458 48V MY25.5][4M][S][1219][CLEA_R5][Climate] 低配车辆，空调页面车模中主驾门上显示腰托按钮，副驾门上显示座椅电动按钮，与实车不一致Low-end vehicles, air conditioning page car model shows lumbar support button on the main driver's door and seat power button on the passenger's door, the real car does not have the corresponding configuration | Resolved 0/4 |  | Always | UI Framework | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 | sq_transferred_1227 | U-Van/358-2/MY25 U-Van/458/MY25.5 | PATAC | 2024-12-27 下午5:13
Bug | 967468 | [458 48V MY25.5][4M][S][1219][CLEA_R5][Climate]重其他界面进入空调界面，概率出现空调界面连续闪烁两次。\If you enter the air conditioner interface, the air conditioner interface will flash twice in a row. | Resolved 3/4 | duplicated | Always | Basic_Module | 2025-2-8 下午4:33 | 2025-2-14 下午12:00 | 蒋建,Jiang Jian | P3 | sq_transferred_1226 | U-Van/458/MY25.5 | PATAC | 2024-12-26 下午5:11
Bug | 966939 | [Drive_Mode][L233][MY23]驾驶模式无法正常切换至防滑和Vmode。/Driving mode does not switch properly to anti-skid and Vmode. | 3/4 Reviewed | duplicated | Always | Framework | 2025-2-12 下午5:56 |  | 蒋建,Jiang Jian | P2 | my26sopunique, rebuild需求问题 | BEV 3/L233/MY23 BEV 3/L233/MY24 | PATAC | 2024-12-25 下午8:31
Bug | 966884 | [Vehicle Setting]实况桌面显示异常 | Resolved 3/4 | duplicated | Once | Vehicle Setting | 2025-1-14 下午2:15 | 2025-2-6 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2024-12-25 下午6:56
Bug | 966703 | [Climate][B233 MY25][Mid]进入空调面板，界面会闪烁一下 Upon entering the air conditioning panel, the interface will flash briefly | Resolved 0/4 |  | Frequent | Basic_Module | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 | lg_transferred_1225 | BEV 3/B233/MY25 BEV 3/B223/MY25 BEV 3/B233/MY24 | PATAC | 2024-12-25 下午4:04
Bug | 966408 | [Vehicle Setting][557][MY26]深浅色切换显示右侧车模显示异常The color switch shows that the car model on the right is abnormal | Resolved 3/4 | fixed | Always | UI Framework | 2025-2-17 下午4:37 | 2025-2-17 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2024-12-25 上午9:53
Bug | 966403 | [Climate][B2X3 8M MY25][R5 HF4][VCU]打开空调/座椅页面，车模UI闪烁/Open the air conditioning/seat page, the car model UI flashes | Resolved 3/4 | duplicated | Frequent | Basic_Module | 2025-2-8 下午2:31 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 | sq_transferred_1225 | BEV 3/B233/MY25 | PATAC | 2024-12-25 上午9:48
Bug | 966036 | [Basic_Module][B233][B223][MY24][MY25][MID]点击Apptray中的空调与座椅，进入后会闪烁上一次进入的图像Click on the air conditioner and seat in the Apptray, and the image of the last entry will flash after entering | Resolved 3/4 | duplicated | Always | Basic_Module | 2025-1-8 下午1:35 | 2025-2-5 下午12:00 | 蒋建,Jiang Jian | P2 | sq_transferred_1225 | BEV 3/B233/MY25 BEV 3/B233/MY24 BEV 3/B223/MY25 | PATAC | 2024-12-24 下午5:11
Bug | 964963 | [Climate][557 MY26][VCUPro][Vescom5.0]断电重新上电空调页面温度闪现HI且车模短暂消失 | Resolved 3/4 | fixed | Always | Basic_Module | 2025-1-17 下午5:10 | 2025-1-17 下午12:00 | 蒋建,Jiang Jian | P2 | sq_transferred_1220, sq_transferred_1224, sq_transferred_0112 | U-Van/557/MY26 | PATAC | 2024-12-20 下午7:43
Bug | 964783 | [Framework][Launcher][557E][MY26]实况桌面显示异常/3D model home display abnormality | Resolved 0/4 |  | Frequent | Framework | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P2 |  | U-Van/557/MY26 | PATAC | 2024-12-20 下午4:14
Bug | 964307 | [Basic_Module][557E][MY26]车模界面尾门button不可用，各buttondisable状态不可用 | Resolved 3/4 | fixed | Always | Basic_Module | 2025-2-10 上午11:20 | 2025-2-10 下午12:00 | 蒋建,Jiang Jian | P3 | sgm_app2_android_platform_neutest | U-Van/557/MY26 | PATAC | 2024-12-19 下午5:50
Bug | 963064 | [CLEA_R5_F1KM][458][MY23][Cluster_ADAS]仪表侧ADAS视图不显示车模（The ADAS view on the instrument side does not display the car model） | 3/4 Reviewed | fixed | Always | Cluster_ADAS | 2025-1-11 上午10:37 | 2024-12-20 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/458/MY23 | PATAC | 2024-12-17 下午4:20
Bug | 961714 | [Cluster_Theme][Cluster_ADAS][CadiRebuild][L232][MY25][mainline]车道线超过地平线，车道线上方有横线 / The lane line exceeds the horizon, and there is a horizontal line above the lane line | Resolved 3/4 | fixed | Always | Cluster_Theme | 2025-2-8 下午7:16 | 2024-12-24 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L232/MY25 Omega/O1SL-2/MY25 BEV 3/L233/MY25 Alpha/A2LL/MY25 | PATAC | 2024-12-13 下午3:24
Bug | 960894 | [HUD][B2X3 4M MY24][R5 HF4][VCU]开启雪地模式HUD中飞机模型未变化颜色\INC Edit status Cannot drag the driving mode icon to the specified location | Resolved 0/4 |  | Always | HUD | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 |  | BEV 3/B223/MY24 BEV 3/B233/MY25 | PATAC | 2024-12-12 上午9:07
Bug | 958650 | [B233/B223 MY24 OTA][Performance]com.patac.hmi.climate run monkey 72h cause native crash | Resolved 3/4 | duplicated | Once | Performance | 2025-2-8 下午3:44 | 2025-2-8 下午12:00 | 蒋建,Jiang Jian | P3 | sq_transferred_1206 | BEV 3/B233/MY24 | PATAC | 2024-12-6 下午1:33
Bug | 957939 | [Performance]climate_tabSwitch性能场景测试中，com.patac.hmi.climate mem超出KPI | Resolved 0/4 |  | Once | Performance | 2025-2-17 上午8:32 |  | 蒋建,Jiang Jian | P4 | lg_transferred_1210 | U-Van/557/MY26 | PATAC | 2024-12-5 上午10:35
Bug | 957005 | [557][MY26][Climate][80BOR]吹风动画偶发卡顿 Occasional lag in blower animation | Resolved 0/4 |  | Once | Climate | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2024-12-3 下午4:37
Bug | 956862 | [557][MY26][Climate][80BOR]吹脚动效颜色和其它吹风模式不同（如吹脸） The color of the foot blower effect is different from other blower modes (ex. vent blower) | Resolved 0/4 |  | Always | Basic_Module | 2025-1-8 下午12:59 |  | 蒋建,Jiang Jian | P3 | sq_transferred | U-Van/557/MY26 | PATAC | 2024-12-3 下午3:36
Bug | 954716 | [System][U-Van/358-2 phev/MY25][clea_r5]下方快捷栏点击空调，在返回主页面，在点击快捷栏座椅图标，会闪一下空调页面在跳到座椅界面。 | Resolved 3/4 | fixed | Always | System | 2025-2-8 下午3:05 | 2024-11-29 下午12:00 | 蒋建,Jiang Jian | P2 | [sil] | U-Van/358-2 PHEV/MY25 | PATAC | 2024-11-28 下午11:12
Bug | 954507 | [HUD][AR][L234][MY26][mainline]服务区POI始终在视野外，且和目的地重叠 / The POI in the service area is always out of sight and overlaps with the destination | 3/4 Reviewed | fixed | Always | HUD | 2025-2-9 下午4:53 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L234/MY26 | PATAC | 2024-11-28 下午5:17
Bug | 952176 | [HUD][AR][L234][mainline]AR HUD 不能触发车道居中辅助ARDO / AR HUD cannot trigger lane centering assist ARDO | Resolved 0/4 |  | Always | HUD | 2025-2-9 下午4:53 | 2025-2-28 下午12:00 | 蒋建,Jiang Jian | P3 |  | BEV 3/L234/MY26 | PATAC | 2024-11-25 下午3:26
Bug | 949059 | [557][Climate][MY26][80BOR]浅色模式，吹风动画显示有误 Light mode, the blower animation is displayed incorrectly | Resolved 3/4 | fixed | Always | Basic_Module | 2025-1-8 下午1:00 | 2024-11-20 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/557/MY26 | PATAC | 2024-11-18 下午5:49
Bug | 947433 | [458 48V MY25][4M][CIP1][1103][CLEA_R5][Ambient_Light] VA调整氛围灯亮度，VA正向回复，实际氛围灯亮度有变化，氛围灯页面亮度条没有响应 VA adjusts ambient light brightness, VA positively replies, actual ambient light brightness changes, ambient light page brightness bar not responding | Resolved 3/4 | duplicated | Once | Ambient_Light | 2025-1-8 下午1:00 | 2024-11-30 下午12:00 | 蒋建,Jiang Jian | P3 |  | U-Van/458/MY25 U-Van/358-2/MY25 U-Van/358-2 PHEV/MY25 | PATAC | 2024-11-14 下午5:08
Bug | 935275 | [557][Climate][MY26]首次进入空调页面较慢 Slow first time entering climate page | Resolved 3/4 | fixed | Always | Basic_Module | 2025-2-19 下午7:48 | 2025-2-19 下午12:00 | 蒋建,Jiang Jian | P3 | sgm_app2_android_platform_systemui, sq_transferred | U-Van/557/MY26 | PATAC | 2024-10-18 下午5:33
Bug | 933532 | [PATAC_Seats][CLEA_R5][MY25][458][4M]切换为浅色模式后座舱页面出现蒙层 Cockpit page appears as a mask after switching to light colour mode | Resolved 0/4 |  | Always | PATAC_Seats | 2025-1-17 下午4:48 |  | 蒋建,Jiang Jian | P3 | zy_transferred, lg_transferred_0106 | U-Van/458/MY25 U-Van/458/MY23 | PATAC | 2024-10-16 下午4:25
Bug | 929594 | [Climate][458 MY25][ R5-0924]hmi-下方快捷栏点击空调再返回主界面再点座椅hmi会闪一下空调页面再跳到座椅界面 9：58//HMI - Click on the air conditioner in the shortcut bar below, then return to the main interface and click on the seat. HMI will flash the air conditioner page and jump to the seat interface at 9:58 | Resolved 3/4 | duplicated | Once | Basic_Module | 2025-2-8 下午5:21 | 2024-10-12 下午12:00 | 蒋建,Jiang Jian | P1 | zy_transferred | U-Van/458/MY25 | PATAC | 2024-10-10 下午4:28
Bug | 922836 | [Performance]压测过程中，Android侧kanziservice进程内存占用均值为502.82MB，峰值为506.01MB，KPI为120MB，不达标[the memory use of kanziservice is over KPI 120MB when running stress auto test] | Resolved 3/4 | fixed | Once | Performance | 2025-1-8 下午1:00 | 2024-9-20 下午12:00 | 蒋建,Jiang Jian | P2 | 65%mustfix | U-Van/557/MY26 | PATAC | 2024-9-19 下午12:28
Bug | 921351 | [FROM_DevVal][358-2 48V MY25] [Vescom 11.0] [HVAC]电动出风口手动情况下，整车休眠唤醒无法存储之前的上下位置/In the case of manual electric outlet, the vehicle sleep wake up cannot store the previous up and down position | Resolved 3/4 | duplicated | Always | Climate | 2025-1-8 下午1:00 | 2024-12-31 下午12:00 | 蒋建,Jiang Jian | P4 | devval, from_comm | U-Van/358-2/MY25 U-Van/358-2 PHEV/MY25 | PATAC | 2024-9-13 下午3:14
Bug | 918892 | [Performance][MY26][557]com.ts.kanziservice进程性能数据超过kpi | Resolved 3/4 | fixed | Frequent | Performance | 2025-2-21 上午9:26 | 2024-9-14 下午12:00 | 蒋建,Jiang Jian | P2 | 65%mustfix | U-Van/557/MY26 | PATAC | 2024-9-10 下午2:49
Bug | 899159 | [FROM_DevVal][E2UB/YB MY24][R5_Hotfix3][VCU Mid][0725] [Ambient_Light]休眠重启或恢复出厂设置后首次进入氛围灯界面，闪现异常车模/Enter the atmosphere light interface for the first time after hibernating and restarting or restoring factory Settings, and the abnormal model flashes | Resolved 0/4 |  | Always | Ambient_Light | 2025-1-8 下午1:00 |  | 蒋建,Jiang Jian | P3 |  | Epsilon/E2YB/MY24 Epsilon/E2UB/MY24 Epsilon/E2LB-2/MY25 E2-2/E2LB-2/MY24 | PATAC | 2024-8-1 下午5:27
Bug | 890257 | [Cluster_ADAS][458 48V][ICE]变道中止触发失败【Lane Change Abort trigger failure】 | 3/4 Reviewed | fixed | Always | Cluster_ADAS | 2025-1-24 下午2:46 | 2024-8-7 下午12:00 | 蒋建,Jiang Jian | P2 |  | U-Van/458/MY25 | PATAC | 2024-7-16 下午3:32
Bug | 883486 | [System][MY26][557]cluster_hmi gpu占用高 | 3/4 Reviewed | fixed | Once | System | 2025-2-19 下午7:52 | 2024-7-29 下午12:00 | 蒋建,Jiang Jian | P4 |  | U-Van/557/MY26 | BOSCH 8255 | 2024-7-1 下午1:50
Bug | 852717 | [Vehicle_Control][358-2PHEV][MY25][CLEA_R5]冷启动后进入车辆常用页面3秒内无车模显示/No car model display within 3 seconds of entering the vehicle's common page after a cold start | Resolved 3/4 | duplicated | Always | Vehicle_Control | 2025-1-8 下午1:00 | 2024-5-30 下午12:00 | 蒋建,Jiang Jian | P4 |  | U-Van/358-2 PHEV/MY25 | PATAC | 2024-5-5 下午3:32
Bug | 849526 | [Vehicle_Control][Vehicle_Info][358][458HEV][MY25][CLEA_R5]设置-车辆-常用页面，点击apptray切换页面，kanzi车模与页面消失时间不一致 | Resolved 0/4 |  | Once | Vehicle_Control | 2025-2-10 上午11:00 | 2025-1-9 下午12:00 | 蒋建,Jiang Jian | P4 |  | U-Van/358-2 PHEV/MY25 U-Van/458 HEV/MY25 U-Van/358-2/MY25 | PATAC | 2024-4-26 下午6:01
Bug | 837365 | [hotfix3][Ambient_Light]重启车机后首次进入氛围灯界面，氛围灯出现延迟The ambient light appears delayed when entering the ambient light interface for the first time after restarting the car. | Resolved 1/4 | fixed | Always | Ambient_Light | 2025-1-20 上午10:46 | 2024-4-26 下午12:00 | 蒋建,Jiang Jian | P3 | hotfixr5 | U-Van/458 HEV/MY25 U-Van/358-2 HEV/MY25 U-Van/358-2 PHEV/MY25 | PATAC | 2024-4-11 上午11:35