## RTC Bug汇总
Type | Id | Summary | Owned By | Status | Tags | Priority | Modified Date | Creation Date | Platform Vehicle Model | 分支车型 | 超期/天（Creation Date） | 计划完成时间 | 进展说明（对应模块的研发更新） | 研发状态开发更新 | R5分支提交date | 主分支提交date | hotfix提交date | 版本时间 | 测试结果 | 签入日期
Bug | 813923 | [Cluster_Warning][B233][B223][E22][MY25][R5_Mainline] alert:77 Trigger failure(触发失败) | 徐卓,xu zhuo | New |  | P2 | 2024-3-13 上午11:29 | 2024-3-13 上午10:58 | Epsilon/E2LB-2/MY25 BEV 3/B223/MY25 BEV 3/B233/MY25
Bug | 813898 | [Cluster_Alert][Clea_R5][358-2 HEV][MY25]3D Model display incompletely | 徐卓,xu zhuo | New |  | P3 | 2024-3-13 上午11:03 | 2024-3-13 上午10:37 | U-Van/358-2/MY25
Bug | 813858 | [Cluster_Warning][B233][B223][E22][MY25][R5_Mainline] alert:2092 Trigger failure(触发失败) | 徐卓,xu zhuo | New |  | P2 | 2024-3-13 上午10:37 | 2024-3-13 上午10:11 | Epsilon/E2LB-2/MY25 BEV 3/B223/MY25 BEV 3/B233/MY25
Bug | 813853 | [Cluster_Warning][B233][B223][E22][MY25][R5_Mainline] alert:2091 Trigger failure(触发失败) | 徐卓,xu zhuo | New |  | P2 | 2024-3-13 上午10:55 | 2024-3-13 上午10:09 | Epsilon/E2LB-2/MY25 BEV 3/B223/MY25 BEV 3/B233/MY25
Bug | 813752 | [Cluster_Warning][B233][B223][E22][MY25][R5_Mainline] alert:572 display wrong message(内容错误) | 徐卓,xu zhuo | New |  | P2 | 2024-3-13 上午9:07 | 2024-3-13 上午8:51 | Epsilon/E2LB-2/MY25 BEV 3/B223/MY25 BEV 3/B233/MY25
Bug | 813750 | [FROM_DevVal][358-2 PHEV/HEV MY25][VeSCoM 2.2][CLEA_R5][VCU][Telltale]INC快捷菜单陡坡缓降开关图标与指示灯显示不一致INC shortcut menu steep hill descent switch icon does not match indicator light display | 王振江,Wang Zhenjiang | New | devval, from_comm | P3 | 2024-3-13 上午10:08 | 2024-3-13 上午8:50 | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25
Bug | 813747 | [FROM_DevVal][358-2 PHEV/HEV MY25][VeSCoM 2.2][CLEA_R5][VCU][Alert]#456‘请握住方向盘’浅色模式下配图小，辅助视图文言看不清#456‘Take Steering' in light color mode with a small picture, auxiliary view text is not readable | 徐卓,xu zhuo | New | devval, from_comm | P3 | 2024-3-13 上午9:51 | 2024-3-13 上午8:45 | U-Van/358-2/MY25 U-Van/358-2 PHEV/MY25
Bug | 813507 | [FROM_DevVal][358-2 MY25][VeSCoM 7.1][VCU] [LCC] LCC指令变道时，VCU显示的图标为绿色实线，没有变为绿色虚线 | 徐卓,xu zhuo | New | devval, from_comm | P4 | 2024-3-12 下午9:11 | 2024-3-12 下午5:00 | U-Van/358-2/MY25
Bug | 813478 | [Cluster_Warning][B233/E22/B223][MY24][R5_hotfix2]]Alter948:文言错误（display wrong message） | 徐卓,xu zhuo | New |  | P2 | 2024-3-12 下午4:44 | 2024-3-12 下午4:34 | BEV 3/B223/MY24 BEV 3/B233/MY24 E2-2/E2LB-2/MY24
Bug | 813474 | [Cluster_Warning][B233][B223][E22][MY25][R5_Mainline] alert:808 display wrong message(内容错误) | 徐卓,xu zhuo | New |  | P2 | 2024-3-12 下午4:42 | 2024-3-12 下午4:30 | Epsilon/E2LB-2/MY25 BEV 3/B223/MY25 BEV 3/B233/MY25
Bug | 813319 | [Multimedia][Audio_Basic][B223][B233][E22][MY25][R5_Mainline] 使用SWC切换歌曲，zone3无popup overlay弹出 / Use SWC to switch songs, zone3 popup no popup overlay pops | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-12 下午2:51 | 2024-3-12 下午2:51 | BEV 3/B223/MY25 Epsilon/E2LB-2/MY25 BEV 3/B233/MY25
Bug | 813315 | [Cluster_Warning][B233/E22/B223][MY24][R5_hotfix2]]触发后备箱warning，然后打开位置灯车模位置灯显示红色（Trigger the trunk WARNING, then turn on the position light car model position light shows red） | 徐卓,xu zhuo | New |  | P2 | 2024-3-12 下午8:22 | 2024-3-12 下午2:48 | BEV 3/B223/MY24 BEV 3/B233/MY24 E2-2/E2LB-2/MY24
Bug | 813255 | [Multimedia][B233/B223][MY24][R5_hotfix2] 切换到网易云音源，nowplaying显示未知歌曲，zone3显示无可播放内容Switching to Netcloud audio, nowplaying shows unknown songs, zone3 shows nothing to play | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-13 上午8:45 | 2024-3-12 下午2:08 | BEV 3/B233/MY24 BEV 3/B223/MY24
Bug | 813214 | [Cluster_Gauge][Mainline][NDLB]zone3不显示卡片，且无法使用SWC切换卡片（zone3 doesn't show cards and can't switch cards using SWC） | 吕闯,lv chuang | New |  | P2 | 2024-3-12 下午3:42 | 2024-3-12 下午1:33 | NDEV/NDLB/MY26
Bug | 813190 | [Cluster_Telltale][SIL][358-2 PHEV] IPC侧经济模式和 EV灯是重叠的 ，还是灰色 | 张彪,zhang biao | New | [sil] | P4 | 2024-3-12 下午1:50 | 2024-3-12 下午1:08 | U-Van/358-2 PHEV/MY25
Bug | 813102 | [GB_R5][ZONE3]无法进入zone3编辑页面 The zone3 edit page cannot be accessed | 吕闯,lv chuang | New |  | P2 | 2024-3-12 上午10:33 | 2024-3-12 上午10:33 | Crossover/C1YB-2/MY25
Bug | 812974 | [FROM_DevVal][E2LB-2 MY25][VeSCoM 3.5][0222][VCU Mid][Cluster]低油量时油量指示灯有重影/The fuel indicator is shadowing when the fuel level is low | 王振江,Wang Zhenjiang | New | devval, from_comm | P2 | 2024-3-12 下午3:43 | 2024-3-11 下午8:17 | Epsilon/E2LB-2/MY25
Bug | 812953 | [FROM_DevVal][VCS NDLB MY26][VesCoM3.0][VCU-Mid][Navigation]Zone3导航到达时间不显示12小时制/Zone3 navigation arrival time does not show 12-hour clock | 丁帆,Ding Fan | New | devval, from_comm, 高德相关问题 | P3 | 2024-3-12 上午10:38 | 2024-3-11 下午7:50 | NDEV/NDLB/MY26
Bug | 812480 | [Cluster_Audio][Audio_Basic][B223][B233][E22][MY25][R5_Mainline] 切换到喜马拉雅儿童时IPC侧zone3显示之前歌手名/ When switching to Himalayan Kids, the IPC side zone3 displays the previous singer's name | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-11 下午1:12 | 2024-3-11 上午10:50 | BEV 3/B223/MY25 Epsilon/E2LB-2/MY25 BEV 3/B233/MY25
Bug | 790880 | [Cluster_Warning][B233][B223][E22][MY25][R5_Mainline] alert:72 Unsynchronised display of text and motion graphics(文言与动效图显示不同步) | 徐卓,xu zhuo | New |  | P2 | 2024-3-12 下午1:22 | 2024-3-8 上午10:18 | Epsilon/E2LB-2/MY25 BEV 3/B223/MY25 BEV 3/B233/MY25
Bug | 790658 | [FROM_DevVal][VCS NDLB MY26][VesCoM3.0][VCU-Mid][Cluster_Alert]禁止通行Alert确认对号显示为错号/The No Access Alert confirmation check number is displayed as an error number | 徐卓,xu zhuo | 3/4 Reviewed | devval, from_comm | P3 | 2024-3-12 下午6:21 | 2024-3-7 下午6:00 | NDEV/NDLB/MY26
Bug | 790604 | [CarPlay][B233/B223][MY24][R5_Hotfix2]未连接carplay,点按SWC上“电话”硬按键，Zone 3区域显示carplay标识/Carplay is not connected, press the Phone hard button on the SWC, the Zone 3 area shows the carplay logo. | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-8 下午1:45 | 2024-3-7 下午5:12 | BEV 3/B223/MY24 BEV 3/B233/MY24
Bug | 790407 | [R5_hotfix1][Cluster_Warning][458]W9308-9314触发后无图片显示/No picture display after W9308-9314 trigger | 徐卓,xu zhuo | Resolved 3/4 | mustfixr5 | P2 | 2024-3-13 上午9:38 | 2024-3-7 下午3:08 | U-Van/458/MY24
Bug | 790393 | [CLEA_R5][Cluster_Warning][358-2][MY25]W9308-9314触发后无图片显示/No picture display after W9308-9314 trigger | 徐卓,xu zhuo | Resolved 3/4 | mustfixr5 | P2 | 2024-3-13 上午9:38 | 2024-3-7 下午2:59 | U-Van/458 HEV/MY25 U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25
Bug | 790301 | [CLEA_R5][Cluster_Warning][358-2][MY25]W9300触发后，图片与文言部分重叠/W9300 triggered, the picture overlaps with the text section. | 徐卓,xu zhuo | Resolved 3/4 | mustfixr5 | P2 | 2024-3-13 上午9:38 | 2024-3-7 下午2:01 | U-Van/358-2 PHEV/MY25 U-Van/458 HEV/MY25 U-Van/358-2/MY25
Bug | 790291 | [ADAS Settings][B233][MY24][R5_Hotfix2] TSM标定为0，限速识别不可用（TSM calibrated to 0, speed limit recognition not available) | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-7 下午4:59 | 2024-3-7 下午1:57 | BEV 3/B233/MY24
Bug | 790269 | [CLEA_R5][Cluster_Warning][358-2][MY25]W9270触发后，图片显示不符,ADAS view下，红色小人显示位置错误/After W9270 triggering, the picture display does not match, under ADAS view, the red villain is displayed in the wrong position. | 徐卓,xu zhuo | Resolved 3/4 | mustfixr5 | P2 | 2024-3-12 上午6:03 | 2024-3-7 下午1:45 | U-Van/458 HEV/MY25 U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25
Bug | 790181 | [Cluster_Warning][E22]导航时Zone3不显示直行指示标志（During navigation, Zone3 does not display straight ahead indicator signs） | 丁帆,Ding Fan | New |  | P2 | 2024-3-11 上午10:35 | 2024-3-7 上午10:38 | Epsilon/E2LB-2/MY25
Bug | 790029 | [FROM_DevVal][358-2 PHEV MY25][VeSCoM 2.2][VCU][Cluster]使用SWC将音源切换为蓝牙音乐和在线音频时，IPC zone3的专辑封面有闪动/When using SWC to switch the audio source to Bluetooth music and online audio, the album cover of IPC zone 3 flashes | 王振江,Wang Zhenjiang | New | devval, from_comm | P4 | 2024-3-8 下午11:31 | 2024-3-6 下午7:18 | U-Van/358-2 PHEV/MY25
Bug | 789781 | [Cluster_Gauge][B233][MY24][R5_Hotfix2] 限速标志限速值与外部圈有部分重叠（Speed Limit Values Partially Overlap with Outer Circle） | 张彪,zhang biao | Resolved 3/4 |  | P3 | 2024-3-13 上午9:39 | 2024-3-6 下午4:05 | BEV 3/B223/MY24 BEV 3/B233/MY24 E2-2/E2LB-2/MY24
Bug | 789737 | [Vehicle_Info]【WAUA1.2】【E2YB/UB】【多媒体】【生产】【实车】【必现】【Rollout】重启后，使用方控切到云听，仪表长时间显示‘正在加载媒体...’ | 王振江,Wang Zhenjiang | New |  | P4 | 2024-3-8 下午1:10 | 2024-3-6 下午3:35 | Epsilon/E2UB/MY24 Epsilon/E2YB/MY24
Bug | 789567 | [Cluster_ADAS][358-2PHEV][CLEA_R5]匝道工况, 在地面的目标位置不显示，期待不高亮显示 【in the working condition of ramp，not show the Target Position】 | 徐卓,xu zhuo | 3/4 Reviewed |  | P2 | 2024-3-12 上午10:34 | 2024-3-6 下午1:44 | U-Van/358-2 PHEV/MY25 U-Van/458 HEV/MY25 U-Van/358-2/MY25
Bug | 789362 | [Cluster_Gauge][Mainline][NDLB]Cluster侧不显示速度，电量，行驶里程（Cluster side doesn't show speed, battery, miles traveled） | 张彪,zhang biao | Resolved 3/4 |  | P1 | 2024-3-12 下午1:59 | 2024-3-6 上午10:15 | NDEV/NDLB/MY26
Bug | 789281 | [Cluster_Telltale]【R5_Hotfix2】IPC 不显示限速标志 IPC does not display speed limit signs | 王振江,Wang Zhenjiang | Resolved 3/4 | gbb_r5hotfix2_ctf, hotfix2r5 | P2 | 2024-3-13 上午9:38 | 2024-3-6 上午9:10 | BEV 3/B233/MY24
Bug | 788680 | [B233][B223][E22][MY25][R5_Mainline]IPC侧不展示Last Trip overlay/The IPC side does not display the Last Trip overlay | 徐卓,xu zhuo | Resolved 3/4 |  | P1 | 2024-3-12 上午6:04 | 2024-3-5 下午2:27 | BEV 3/B223/MY25 BEV 3/B233/MY25 E2-2/E2LB-2/MY24
Bug | 788656 | [Cluster_Zone2][Multimedia][B233/B223][MY24][R5_hotfix2] 选择carlink音源，nowplaying界面显示未知歌曲，zone3没有内容显示Selecting carlink source, nowplaying interface shows unknown song, zone3 has no content to display | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-12 下午1:46 | 2024-3-5 下午2:07 | BEV 3/B233/MY24 BEV 3/B223/MY24
Bug | 788425 | [Cluster_Telltale][B233][MY24][R5_Hotfix2] 冷启动，Telltale自检不显示（Cold boot, Telltale blub check not displayed） | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-6 下午1:57 | 2024-3-5 上午10:36 | BEV 3/B223/MY24 BEV 3/B233/MY24 E2-2/E2LB-2/MY24
Bug | 788023 | [CLEA_R5][Cluster_Navi][MY25]当首次发起导航，仪表侧TBT卡片到达时间显示为Text The IPC-side TBT card arrival time is displayed as Text when navigation is first initiated | 丁帆,Ding Fan | New | 六系地图问题 | P4 | 2024-3-7 上午10:20 | 2024-3-4 下午4:57 | U-Van/358-2 PHEV/MY25 U-Van/358-2/MY25 U-Van/458 HEV/MY25
Bug | 787666 | [Theme][NDLB][Mid]切换默认主题失败 Switching default theme failed | 王振江,Wang Zhenjiang | Resolved 3/4 |  | P2 | 2024-3-8 下午4:47 | 2024-3-4 上午11:06 | NDEV/NDLB/MY26
Bug | 759993 | [Cluster General]地图视图 view name字段下方提示“长按此键可编辑仪表右侧区域” Long press this key to edit the right area of the meter below the view name field in the map view | 徐卓,xu zhuo | Resolved 3/4 |  | P2 | 2024-3-4 下午7:56 | 2024-3-1 下午5:44 | Crossover/C1YB-2/MY25
Bug | 759959 | [Cluster_Audio]oncall打断incoming call的显示 oncall interrupts the display of incoming call | 王振江,Wang Zhenjiang | 3/4 Reviewed |  | P2 | 2024-3-11 上午10:27 | 2024-3-1 下午5:14 | Crossover/C1YB-2/MY25
Bug | 759770 | [Cluster_Audio]zone3区域不显示Audio Nowplaying Popup - Overlay The zone3 area does not display Audio Nowplaying Popup-Overlay | 吕闯,lv chuang | 3/4 Reviewed |  | P2 | 2024-3-12 下午1:56 | 2024-3-1 下午3:22 | Crossover/C1YB-2/MY25
Bug | 759748 | [FROM_DevVal][VCS NDLB MY26][VesCoM3.0][VCU-Mid][Cluster_Alert]胎压过低或过高Alert只有文字显示/Under- or over-pressure Alerts are only text-based | 徐卓,xu zhuo | 3/4 Reviewed | devval, from_comm | P3 | 2024-3-8 下午5:01 | 2024-3-1 下午3:03 | NDEV/NDLB/MY26
Bug | 759742 | [CLEA_R5][Cluster_Warning][MY25]W43触发后先显示车模前部，再转到后部/Unclear display of text color in light mode | 徐卓,xu zhuo | New |  | P2 | 2024-3-12 上午9:30 | 2024-3-1 下午3:01 | U-Van/358-2 PHEV/MY25 U-Van/458 HEV/MY25 U-Van/358-2/MY25
Bug | 759658 | [FROM_DevVal][VCS NDLB MY26][VesCoM3.0][VCU-Mid][Navigation]Zone3显示导航到达时间后面没有到字/Zone3 shows that there is no word after the navigation arrival time | 丁帆,Ding Fan | New | devval, from_comm, 五系地图问题 | P3 | 2024-3-1 下午2:51 | 2024-3-1 下午2:06 | NDEV/NDLB/MY26
Bug | 759605 | [CarPlay][B233][B223][E22][MY25][R5_Mainline][mid]播放carplay音乐仪表侧无任何显示Play carplay music no display on dash side | 王振江,Wang Zhenjiang | New |  | P2 | 2024-3-8 上午10:28 | 2024-3-1 下午1:14 | Epsilon/E2LB-2/MY25
Bug | 756373 | [Cluster_Zone2][NDLB MY26]能耗曲线页面Y轴数值显示错误 On Energy Consumption page， scale value of the Y-axis is incorrect | 吕闯,lv chuang | Resolved 3/4 |  | P3 | 2024-3-9 上午10:33 | 2024-2-29 下午6:21 | NDEV/NDLB/MY26 Crossover/C1YB-2/MY25
Bug | 755492 | [Cluster_Zone2][NDLB MY26]胎压学习界面无法触发Tire Pressure Sensor Programming cannot be actived | 吕闯,lv chuang | Resolved 3/4 |  | P3 | 2024-3-13 上午11:12 | 2024-2-29 下午4:19 | NDEV/NDLB/MY26 Crossover/C1YB-2/MY25
Bug | 755482 | [Cluster_Zone2]胎压卡片进入编辑页面无法超时退出 The tire pressure card cannot exit from the editing page | 吕闯,lv chuang | Resolved 0/4 |  | P2 | 2024-3-13 上午9:43 | 2024-2-29 下午4:17 | Crossover/C1YB-2/MY25
Bug | 753576 | [Cluster_Telltale][GB主分支]Indicator #22 无法触发滑移门效果 Indicator #22 does not trigger sliding door effect | 王振江,Wang Zhenjiang | Resolved 3/4 |  | P3 | 2024-3-13 上午9:15 | 2024-2-28 下午3:28 | Crossover/C1YB-2/MY25
Bug | 752260 | [Clea R5][358-2 HEV/358-2 PHEV/458 HEV][MY25][Smoke Test][Theme]主题设置失败（Theme setting failed） | 王振江,Wang Zhenjiang | Resolved 3/4 | mustfixr5 | P2 | 2024-3-8 下午4:47 | 2024-2-27 上午10:33 | U-Van/358-2 PHEV/MY25 U-Van/458 HEV/MY25 U-Van/358-2/MY25
Bug | 752248 | [Cluster_Zone1][NDLB][Mid]大灯背景图显示异常（显示黑色） Abnormal display of headlight background image (black) | 余红文,Yu Hongwen | Resolved 0/4 |  | P2 | 2024-3-7 下午2:31 | 2024-2-27 上午10:27 | NDEV/NDLB/MY26 Crossover/C1YB-2/MY25
Bug | 751977 | [Cluster_Zone1][NDLB][Mid]浅色模式下，大灯背景未变成浅色模式 In light mode, the headlight background has not changed to light mode | 余红文,Yu Hongwen | 3/4 Reviewed |  | P2 | 2024-3-8 下午5:01 | 2024-2-26 下午4:43 | NDEV/NDLB/MY26 Crossover/C1YB-2/MY25
Bug | 751776 | [FROM_DevVal][VCS NDLB MY26][VesCoM3.0][VCU-Mid][VCU-High][浅色模式][Cluster]浅色显示模式下zone1字体和zone3区域warning字体显示不清晰。/In light display mode, the ZONE1 and ZONE3 warning fonts are not displayed clearly. | 余红文,Yu Hongwen | 3/4 Reviewed | devval, from_comm | P2 | 2024-3-6 下午12:50 | 2024-2-26 下午1:10 | NDEV/NDLB/MY26
Bug | 751774 | [FROM_DevVal][VCS NDLB MY26][VesCoM3.0][VCU-Mid][VCU-High][浅色模式][Cluster]浅色显示模式下zone1区域大灯和zone3区域warning出现黑色方块。/In light display mode, black squares appear in the zone1 headlights and zone3 warning. | 余红文,Yu Hongwen | 3/4 Reviewed | devval, from_comm | P2 | 2024-3-12 下午8:05 | 2024-2-26 下午1:08 | NDEV/NDLB/MY26
Bug | 732569 | [Cluster_Peek-In][B233][MY24][R5_Hotfix2] 充电页面不显示zone1（Peek in page does not show zone1） | 余红文,Yu Hongwen | Resolved 0/4 |  | P3 | 2024-3-12 下午5:12 | 2024-2-22 下午3:54 | BEV 3/B223/MY24 BEV 3/B233/MY24 E2-2/E2LB-2/MY24
Bug | 726791 | [Multimedia][B233/B223][MY24][R5_hotfix2] ipc标准视图，导航过程中切换歌曲，ipczone3不显示媒体信息ipc standard view, switching songs during navigation, ipczone3 doesn't show media information | 王振江,Wang Zhenjiang | Resolved 3/4 | hotfix2r5 | P2 | 2024-3-13 上午9:38 | 2024-2-19 下午4:25 | BEV 3/B233/MY24 BEV 3/B223/MY24
Bug | 725437 | [FROM_DevVal][358-2 PHEV MY25][VeSCoM 2.0][VCU][View]地图视图切换至辅助视图，视图短暂重叠显示Map view switches to assist view, views are briefly overlaid | 丁帆,Ding Fan | New | devval, from_comm | P3 | 2024-2-6 上午10:53 | 2024-2-5 下午3:15 | U-Van/358-2 PHEV/MY25
Bug | 712199 | [FROM_DevVal][E2UB/YB MY24][VeSCoM 16.0][Mid_SDV][Phone]通话中切换连接类型（蓝牙&Carplay），IVI和zone3通话时间显示错误/Switching connection type (bluetooth & Carplay) during a call, IVI and zone3 talk time display incorrectly | 王振江,Wang Zhenjiang | Resolved 3/4 | devval, from_comm | P3 | 2024-3-13 上午2:33 | 2024-2-2 上午12:29 | Epsilon/E2UB/MY24 Epsilon/E2YB/MY24
Bug | 703154 | [Cluster_ADAS][E2YB/UB][MY24][R5]限速标识数值与边框重叠(Speed limit sign values overlap the border) | 张彪,zhang biao | 3/4 Reviewed |  | P3 | 2024-3-12 上午9:23 | 2024-1-31 下午2:39 | Epsilon/E2YB/MY24 Epsilon/E2UB/MY24
Bug | 701682 | [FROM_DevVal][358-2 PHEV MY25][358-2 HEV MY25][VeSCoM 2.0][VCU][Cluster]地图视图休眠，唤醒车辆进入ACC模式，地图加载完成后，IPC侧背景会显示地图，与其他重叠显示Map view hibernates, wakes the vehicle into ACC mode, map loading is complete, map is displayed in the background on the IPC side, overlapping with other displays | 丁帆,Ding Fan | Resolved 3/4 | devval, from_comm | P2 | 2024-3-11 下午3:31 | 2024-1-29 上午11:47 | U-Van/358-2/MY25 U-Van/358-2 PHEV/MY25
Bug | 680439 | [Theme][MY25][C1YB-2]默认主题应用失败Default theme application failed | 王振江,Wang Zhenjiang | Resolved 3/4 |  | P2 | 2024-3-7 下午11:50 | 2024-1-4 下午3:26 | Crossover/C1YB-2/MY25
Bug | 679781 | [Cluster_Zone2][E2UB/YB MY24][E2E Test][VCU][mid]EU24OV123 CarPlay 导航切换到百度导航后，IPC Zone3不显示转弯信息 When CarPlay navigation is switched to Baidu navigation, IPC Zone3 does not display turn information | 丁帆,Ding Fan | Resolved 3/4 | integration_test, 桂东处理 | P2 | 2024-3-12 上午9:31 | 2024-1-4 上午8:59 | Epsilon/E2UB/MY24 Epsilon/E2YB/MY24
Bug | 647222 | [FROM_DevVal][B233 MY25][VeSCoM 2.0][VCU High][Cluster]从仪表视图切换为地图视图时，Zone2信息与地图视图略微重叠When switching from gauge view to map view, the Zone2 information overlaps slightly with the map view | 丁帆,Ding Fan | 3/4 Reviewed | devval, from_comm | P3 | 2024-2-22 上午11:02 | 2023-12-13 下午7:25 | BEV 3/B233/MY25 BEV 3/B223/MY25
Bug | 599205 | [Cluster_Navi][458][MY24][R5]仪表非地图模式下，路口放大图显示有误（和UI效果图不符）IPC side junction zoomed-in view is displayed incorrectly (does not match the UI rendering) | 丁帆,Ding Fan | 3/4 Reviewed |  | P4 | 2024-3-6 上午10:42 | 2023-12-1 下午6:11 | U-Van/458/MY24